## Slide 1
{{DECK_TYPE}}
{{CLIENT}}
{{ENGAGEMENT}}
{{DATE}}
PREPARED FOR
© 2026 AlignHCM · Confidential
Align HCM · 01

## Slide 2
{{CLIENT}} · {{ENGAGEMENT}}
Executive Summary
{{CLIENT}} is bringing approximately {{COUNT}} employees onto the existing {{TARGET_PLATFORM}} environment, migrating them off {{SOURCE_PLATFORM}}.
{{COUNT}} employees, {{SOURCE_PLATFORM}} to {{TARGET_PLATFORM}}
{{COUNT}} employees at {{CLIENT}} move from {{SOURCE_PLATFORM}} onto the existing {{TARGET_PLATFORM}} environment.
Existing business rules apply
{{CLIENT}} employees will be set up under the existing business rules, pay rules, and accrual rules already in production.
Scope: Pro, {{WORKSTREAM}}, data & onboarding
Project management, {{TARGET_PLATFORM}} / {{WORKSTREAM}} system configuration, and data conversion.
16-week timeline
12 weeks of implementation plus 4 weeks of post go-live support, targeting a {{GO_LIVE}} go-live (actual go-live is the first pay in January and first punch on the first day of that pay period).
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 02

## Slide 3
16 WEEKS TO GO-LIVE
Proposed Timeline
16 weeks total: 12-week implementation + 4 weeks of post go-live support.
Kickoff &
Planning
Wk 1-2
Analysis &
Validation
Wk 2-5
Configuration
& Build
Wk 4-8
Data
Conversion
Wk 7-10
Testing &
UAT
Wk 9-11
Post Go-Live
Support
Wk 13-16
GO-LIVE
Week 12
Weeks 1-12 · Implementation
Weeks 13-16 · Post Go-Live
Target go-live: {{GO_LIVE}}, with true go-live defined as the start of the first supported pay period.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 03

## Slide 4
PHASE BY PHASE
Milestones by Phase
What gets delivered, and when, across the 16-week engagement.
Phase | Weeks | Key Milestones
Kickoff & Planning | Wk 1-2 | Project kickoff, team alignment, environment access, project plan finalized
Analysis & Validation | Wk 2-5 | Validate the {{CLIENT}} population against existing business, pay, and accrual rules; confirm component company structure
Configuration & Build | Wk 4-8 | Component company setup in {{TARGET_PLATFORM}}, {{WORKSTREAM}} configuration walkthroughs, integration updates
Data Conversion | Wk 7-10 | Convert and load {{CLIENT}} employee data from {{SOURCE_PLATFORM}}; validate demographic, pay, and accrual data
Testing & UAT | Wk 9-11 | Parallel payroll testing, user acceptance testing, sign-off
Go-Live | Wk 12 | {{CLIENT}} employees live on {{TARGET_PLATFORM}}; first supported payroll processed
Post Go-Live Support | Wk 13-16 | Hypercare support, issue resolution, transition to steady state
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 04

## Slide 5
PHASE 1 INVESTMENT
AlignHCM — Planned Investment
Total project cost for a {{GO_LIVE}} go-live.
{{PRICE}}
Total project investment · {{GO_LIVE}} go-live
Includes project management, {{TARGET_PLATFORM}} & {{WORKSTREAM}} system configuration, and employee data conversion.
+{{FEE}} for an earlier go-live
If {{CLIENT}} goes live sooner than {{GO_LIVE}}, an additional {{FEE}} applies for the extra data conversion work required to bring over opening balances.
12 weeks of implementation + 4 weeks of post go-live support = 16 weeks total
Pricing reflects Phase 1 only: bringing {{COUNT}} employees at {{CLIENT}} onto the existing {{TARGET_PLATFORM}} environment. Phase 2 ({{PHASE_2_SCOPE}}) will be scoped and priced separately.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 05

## Slide 6
YOUR TEAM'S ROLE
What We'll Need From Your Team
Estimated level of engagement by project phase.
Resource | Kickoff | Analysis | Build & Convert | Test | Go-Live
Project Lead | Medium | Medium | Medium | Medium | Low
HR / Payroll SME | Low | High | Medium | High | Medium
System Administrator | Low | Medium | High | Medium | Medium
IT / Data Contact | Low | Low | High | Low | Low
Your team stays focused on decisions and validation
The {{CLIENT}} team confirms that {{CLIENT}} employees fit existing business rules, validates converted data, and supports UAT sign-off. AlignHCM leads configuration, data conversion, and testing coordination.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 06

## Slide 7
NEXT STEP
Let's stay connected!
{{ALIGN_CONTACT}}
Client Executive
{{CONTACT_EMAIL}}
{{CONTACT_PHONE}}
alignhcm.com
© 2026 AlignHCM · Confidential · 07